## Slide 1
PM view of SAFe
SAFe Construction Planning Workshop
A J Casson
2nd October 2017

## Slide 2
All review participants agreed that:
Agile is a misunderstood term.
The company environment has to be ready: customer access and effort, senior management support, a good team and flexible culture.
Multi-function people and co-location are ideal.
Communications and ways of working take more effort with agile than waterfall: invest in team building and designing processes upfront.
Self-organising teams need help: environment, support and access to the customer.
It’s all about delivering small but delivering often.
Planning and reviews have to be done but can be fun.
Measure and track! It’s important to get metrics for visibility as well as control.
The Association for Project Management on the Practical Adoption of Agile Methodologies

## Slide 3
Top level SKA1 Construction WBS:
The project as a whole is a waterfall (phase gate) project whereby we proceed through phases linearly: concept  requirements  preliminary design  detailed design & development  procurement  construction/manufacturing  shipping  contractor’s assembly, integration & verification on site  system AIV  handover to operations
Because the software in particular is high risk it makes sense to use a more agile approach such as SAFe during the Construction phase and beyond
SAFe will apply only to parts of 1.4 Computing & Software
However, the 3 monthly Program Increment cadence will apply to the whole of the construction project delivery
SKA Context
1.1 Project Office
1.2 MID Telescope
1.3 LOW Telescope
1.4 Computing & Software
1.5 Verification
1.6 Integrated Logistic Support

## Slide 4
1.4 Computing and Software
  1.4.1 SKA Software Solution Support
  1.4.2 Science Data Processor
    1.4.2.1 SDP Software Programme Support
    1.4.2.2 SDP Agile Team 1
  1.4.3 Telescope Manager
    1.4.3.1 TM Software Programme Support
    1.4.3.2 TM Agile Team 1
  1.4.4 Central Signal Processor Common
    1.4.4.1 CSP Common Programme Support
    1.4.4.2 PSS Delivery
    1.4.4.3 PST Delivery
    1.4.4.4 LMC Delivery
  1.4.5 Element LMC and Common Software
    1.4.5.1 Element LMC and Common Software Programme Support
    1.4.5.2 Element LMC and Common Software Agile Team 1
  1.4.6 Computing Procurement Support
WBS: 1.4 Computing & Software (incomplete)
SAFe Solution layer: Office performed work
SAFe Programs: work performed by Contractors
with multiple agile teams within each program
Non-SAFe Office performed work

## Slide 5
1.4 delivers into 1.2 (Mid Telescope), 1.3 (Low Telescope) and 1.5 (Verification) at appropriate times and with appropriate scopes to meet the Mid and Low Roll-out Plans
The telescopes only take software releases when they need to (on demand), not every sprint nor every Program Increment
All parts of the WBS will be represented at some level at each Program Increment meeting to share status and issues, help prioritise next PI etc.
Assumptions

## Slide 6
Process | Currently in Pre-Construction | Changes in Construction | SAFe specific change?
Scope management | Statements of Work, applicable documents such as L1 requirements and Baseline Design controlled by ECP process | New SoWs and applicable documents managed via contracting process | No
Planning & control | Consortia manage within their scope, at Pre-Construction workpackage level Office manages at project level Formal and informal progress meetings and reviews Milestone reviews and certificates leading to earned value Management reporting (Dashboard, Board reports, reports to SEAC, StratCom, Finance Committee etc) | Contractors manage within their scope, at contract level Office manages at project level Align some progress meetings with Program Increment meetings Milestone reviews leading to earned value or payment by milestone Reports to IGO Council & appropriate committees | No No Partly - timing Partly - 1.4 value measurement TBD Partly – some new metrics needed for 1.4
Resourcing | Office & Consortia roles and responsibilities defined in PMPs, change of key consortia roles subject to Office agreement | New Office PMP; contractor key roles agreed and managed via contracting process | Partly – new SAFe roles & training needed
Cost control | Consortia partners manage their own budgets; Office manages its own budget | Office manages cost cap budget whether cash or in-kind, and manages own budget | No
PM Processes 1

## Slide 7
Process | Currently in Pre-Construction | Changes in Construction | SAFe specific change?
Schedule management | Consortia manage own schedules within overall project schedule Office tracks key milestones including element level reviews, key dependencies including ICDs, and own milestones including system level reviews | Contractors manage own schedules within overall project schedule Office tracks key milestones and dependencies and reviews PI meetings increase visibility | Partly – PI cadence, release on demand flexibility
Communications | Progress meetings & reports, CL meetings, Confluence/collaboration spaces, PM Forum, SKA website, IETs, JIRA, CCB, Telescope Teams, Board papers… | Change from consortia to contractors will mean contract reviews replace some current methods, IGO Council replaces Board, other changes to be confirmed | Partly – PI meetings, 1.4 common software tools
Risks and issues | Consortia manage these at element level and escalate via progress & risk reports Office manages these at project level and escalate via Dashboard, PB Issue Log, Risk Review, Red Flags and Board reports | Contractors manage these within their contracts Contract reviews and IGO Council reports form parts of escalation paths | Partly – PI meetings help identify, 1.4 prioritised backlogs address
Change management | Consortia manage within their scope Office manages system level changes | Contractors manage within their scope Office manages project level changes | No
Lessons Learned | Captured for PDRs, via deliverable reviews, progress meetings etc | Contract reviews, PI meetings | Partly – sprints and PIs feedback
PM Processes 2

## Slide 8
We’ll be running a waterfall project with an agile part
The increased transparency and flexibility SAFe gives us wrt the software delivery should be beneficial
The agile cadence affects the wider project
This cadence gives us opportunities to improve communications, increase engagement, dispel misconceptions, uncover issues earlier etc.
Some PM processes will need to change, but they are changing anyway for Construction
More thinking is needed, particularly around roles and responsibilities, tools and reporting
Summary

## Slide 10
The Work Breakdown Structure (WBS) defines the entire scope of the SKA1 Construction project and so covers all the work needed:
  Office project and engineering management
  construction of the elements via in-kind or commercial contracts
  host country deliverables
It therefore covers the delivery of the entire Product Breakdown Structure (PBS) and also includes all the management activities
Top level SKA1 Construction WBS:
Work Breakdown Structure
1.1 Project Office
1.2 MID Telescope
1.3 LOW Telescope
1.4 Computing & Software
1.5 Verification
1.6 Integrated Logistic Support

## Slide 11
Construction Schedule (using ROP v5)
MID System ITF Qualification Testing Completed | 18/07/2022
MID AA1 Integration and Verification Completed | 11/09/2023
MID AA2 Integration and Verification Completed | 07/07/2024
MID AA3 Integration and Verification Completed | 03/05/2025
MID AA4 Integration and Verification Completed | 27/02/2026
LOW System ITF qualification testing completed | 17/08/2022
LOW AA1 integration and verification completed | 10/11/2023
LOW AA2 integration and verification completed | 05/09/2024
LOW AA3 integration and verification completed | 03/05/2025
LOW AA4 integration and verification completed | 27/02/2026
AR1 8 dishes
AR2 64
AR3 128 (incl. 8 MK)
AR4 197 (incl. 64 MK)
ITF QE 4 stations
AR1 18 stations
AR2 64
AR3 256
AR4 512