## Slide 1: SKA Monitoring and Control CoDR Panel Report
Peter Dewdney (SPDO)
Jo Lister (CRPP-EPFL) (chair)
Gianni Raffi (ALMA)
Vinay Vaidya (KPIT Cummins)
Sonja Vrcic (NRC-CNRC)
Andreas Wicenec (ICRAR)
10 November 2011

## Slide 2: M&C CoDR Overall reactions
The logistics were excellent, warmly recognised by the panel members who had travelled far.
This CoDR therefore took place in very good and amicable conditions.
The panel recognises the high standard of the documents prepared for the CoDR and also that of the presentations made by the M&C team.
The documents were all provided on time for the panel review.

## Slide 3: M&C CoDR Overall reactions
The team is also congratulated for the high technical content of the documentation, supported by the clarifications during the design process
The panel wishes to raise a number of general issues following general observations before reporting on the specific CoDR charges
The panel only identified a few gaps – sorry….

## Slide 4: M&C CoDR Scope and positioning
The panel discussed the role and scope in depth, as did the review meeting. The meeting and project understood the various issues and followed them closely.
The panel’s view can be expressed summarily as:
The M&C aspect of the project encompasses many different technologies and interfaces (e.g. embedded systems, signal transport, operations, real time, etc.).
A critical aspect of M&C is the software, a technology that cuts across many aspects and components of the system.
The challenges associated with this project choice should not be understated
The panel strongly suggests the creation of a project-wide computing governance body reporting to project management.
Such a body would oversee all computing governance issues such as:
  Standards, frameworks, data model, databases, data formats, networks, computer hardware, archiving, operating systems, languages, HPC, tools, performance, science analysis tools, IT, testing, methodology, releases,….

## Slide 5
Users
GUIs
SDS
M&C
Analysis
Net
Tim
ALMA, monolithic 3 suppliers
Users
GUIs
SDS
M&C
Analysis
Net
Tim
ITER, not in-kind
Users
GUIs
SDS
M&C
Analysis
Net
Tim
SKA??
In-kind
Recommendation
Project-wide
Standing committee
“Computing Governance”
SKA

## Slide 6: M&C CoDR Overall reactions
The panel attempted to develop a revised view of M&C scope, and will pursue this for the report

## Slide 7: M&C CoDR Overall reactions
Effort estimate | The panel was not convinced by the effort estimate and were unanimous in considering it a risky underestimate. The panel suggests that multiple additional software houses be asked to estimate the level of effort to achieve the same goals. The panel feared that the estimate had factored in R&D working methods and initial project zeal. The panel also recognised that the effort required is a function of the design options chosen during the design phase, and can only be rough.
Scope and positioning | This project issue was well aired and the summary by Yashwant Gupta recognised this issue. The panel will express its views on the issues and risks in their report
Safety | The panel noted the non-uniform treatment and definitions of safety and recognised that this was taken on board by the M&C Team

## Slide 8: M&C CoDR Overall reactions
Working assumptions | The M&C team was recognised to have made working assumptions with project-wide implications, which is of value to the project, but such assumptions will have to be decided at the project level before flowing back down as system design assumptions.
Project phasing | M&C has the requirement to be functional before the first commissioning of infrastructure. This requires it to advance faster than other Elements. There is a strong risk that the other Elements will catch up by inventing new requirements. The architecture will then be adapted to fit, leading to non-optimal solutions.
Long development time | The long development time brings challenges such as persistence of zeal, staff churn and SW/HW obsolescence, which should appear in the management approach (IEC)

## Slide 9: M&C CoDR Overall reactions
How to handle a distributed team | Imposing strict SE methodology imposes important procedures (risks, requirements, use cases), but does not mitigate the "single brain" requirement of any project
Architecture options | The two options are not considered to be competitors and the "service capability" might be overlaid on the conventional hierarchical model - recognised by the M&C team
Peer telescopes | The panel recognised the usefulness of the ASKAP, MeerKAT and LOFAR contributions to the review meeting and strongly recommends that the M&C team maintains close contact with the developments of the three projects during the next SKA phase and share a maximum of available experience and data.

## Slide 10: M&C CoDR Charge #1
Are the requirements complete, and sufficiently defined for this stage of the project ?
  No, not compared with what they need
  The derived M&C requirements are appropriate
A serious push on the overall system requirements is necessary to support the current rate of progress of M&C, and to avoid overdoing working-assumptions

## Slide 11: M&C CoDR Charge #2
At the concept level, is the M&C presented capable of meeting the requirements ?
  The M&C group presented a very complete understanding at the conceptual level
  No show stoppers were identified given the existing requirements
  A large number of issues to be analysed in the next phase was identified by the M&C team documented in the panel report

## Slide 12: M&C CoDR Charge #3
Have interfaces to other aspects of the system been adequately identified and defined at this stage of the program ?
  No, these are missing at the project level.
  The M&C group has been very creative in anticipating working assumptions on interfaces to move forwards. These will have to be validated at the project level.

## Slide 13: M&C CoDR Charge #4
Are the options proposed to be carried forward credible and are the presented data and information in support of each option credible?
  The options are considered credible
  This judgement is supported by state of the art usage, but the missing non-functional incoming requirements do not allow us to confirm credibility
  The panel agreed on the hierarchical approach being the baseline, but encourages the M&C team to pursue encapsulating some specific features of the “service oriented” model

## Slide 14: M&C CoDR Charge #5
Have all the necessary aspects of the M&C been considered and addressed during the review or are there gaps and/or shortcomings?
  The panel noted that all issues raised during the meeting had been raised in the documentation, with the noted exception of safety

## Slide 15: M&C CoDR Charge #6
Does the risk profile appear reasonably detailed and assessed for this stage of the program ?
  The system risk profile is extensive, appropriate and on the way to completion
  The M&C risk profile contains missing links upwards, presented by the M&C team
  The work is appropriately advanced

## Slide 16: M&C CoDR Charge #7
Do the stated risk controls and proposed mitigations appear reasonable and executable ?
  The panel noted that some mitigation relied on System Engineering solving “all” problems and warned that SE solves a very wide range of problems, but not all problems.
  The geographical separation of the project as a whole is not adequately solved by a paper trail and will require significant travel to ensure harmony long term. Video conferencing supports work in progress effectively, but does not enhance mutual understanding. M&C has many interfaces and therefore travel will be relatively costly, as exposed by the M&C team.
  There might be a conflict between the early required M&C functionality and the evolution of the full project requirements and interfaces

## Slide 17: M&C CoDR Charge #8
Is the overall plan (including identification of the tasks, effort, resources, costs, schedule and risk mitigation needed) to complete the project phases credible ?
  The panel expressed a strong reserve on the M&C team estimate of effort for the phases presented and asks how much optimism was factored in
  The design and construction of M&C up to a functional system for early infrastructure commissioning should be explicitly resourced
  Technically, provided the requirement downflow is available on time, the M&C team should meet its technical goals within the time allotted
  Meeting the intermediate project review goals does not appear to present a difficulty if adequate resources are available

## Slide 18: M&C CoDR Last words
The panel would like to express their gratitude for the warm welcome and for the quality of the logistics arrangement.
The panel is well aware of the extremely high level of activity which precedes a CoDR and congratulates them on hitting the target.
The panel wishes them a fruitful programme heading for the future
SRR Requirements review
PDR Preliminary design review
CDR Critical design review
PR Production review
AR Acceptance review
And then, finally, the pleasure of the SKA!!!