## Slide 1: SKA Signal & Data Transport Synchronisation & Timing Interface Workshop Summary of Bilaterals

## Slide 2: SADT Overall Summary
Total ICD count is currently 37 system level ICDs across 6 Elements
LFAA 3 ICDs
DISHES 7 ICDs
CSP 12 ICDs
TM ? Unable to proceed
SDP 10 ICDs
INFRA At least 3 ICDs (one per telescope)
AIV 2 ICD confirmed for SAT
        2 possible ICDs for Site Network (TBC)

## Slide 3: SADT Interface Summary
LFAA Baseline + LFAAA design differences, location of beam former/CSP - Architecture
        Unlikely to resolve how we connect to the LFAA until PDR?
DISHES Timing interface boundaries need to be defined by T0+12 weeks. This will drive verification.
        Location of beam former/CSP needs to be decided to proceed with work - Requirements
CSP CSP remote access network – who own this? Architecture
  Maintenance / policing / governance and security of network integrity – Requirements
TM No clear definition of top level architecture. Architecture
Unable to proceed with interface definitions
  Maintenance / policing / governance and security of network integrity – Requirements
SDP Locations of SDPs unclear – will affect interfaces – Requirements Architecture
        Inclusion of S.A. NIP as a separate interface from CSP is news to SADT
                SDP have no flexibility in defining I/F protocols – steered by Industry
                Maintenance / policing / governance and security of network integrity – Requirements
INFRA Require SKA topology, location of CSPs (both sites), & SDP in S.A., - Architecture
Accommodation of BMS network is new – implications TBD.
Need visibility of redundancy requirements from Con Ops, Con Ops
Need explicit visibility of SKA 2 support requirement – cost implications Requirements
AIV Architecture uncertainty wrt high frequency phase distribution Architecture
ICDs for existing precursor clocks still in work.
ICD requirement for site network TBC (may be with TM instead of AIV)