## Slide 1: SKAO Project Update
P.Diamond, SKAO Director-General
27 September 2022

## Slide 2: 21st Century Astronomy
LUVOIR-B
ngVLA

## Slide 3: SKAO Membership
The Square Kilometre Array Observatory (SKAO)
An inter-governmental organization, governed by a treaty. SKAO was born on 4th February 2021.
Early stages
Interim agreements
Membership negotiations
Accession stage
Full membership
Australia, China, Italy, Netherlands,
Portugal, South Africa, Switzerland, UK
France, Spain
Germany
Canada, India, Sweden
Japan, South Korea

## Slide 4
Notes: In the past 12 months:
-

## Slide 5: What are we building? One Observatory, Two Telescopes, Three Sites
SKA-HQ Jodrell Bank, UK
Sites selected for their radio quietness  low population density
Total project cost: ~€2.1B; operational in 2029/2030

## Slide 6: Selecting the sites
SKA Mid
SKA Low

## Slide 7: Array configurations in South Africa and Australia
150 km extent
74 km extent

## Slide 8: Some of the big SKA Science questions
The Cradle of Life & Astrobiology
  How do planets form? Are we alone?
Strong-field Tests of Gravity with Pulsars and Black Holes
  Was Einstein right with General Relativity?
The Origin and Evolution of Cosmic Magnetism
  What is the role of magnetism in galaxy evolution and the structure of the cosmic web?
Galaxy Evolution probed by Neutral Hydrogen
  How do normal galaxies form and grow?
The Transient Radio Sky
  What are Fast Radio Bursts and how can we best utilise them? What haven’t we discovered?
Galaxy Evolution probed in the Radio Continuum
  What is the star-formation history of normal galaxies?
Cosmology & Dark Energy
  What is dark matter? What is the large-scale structure of the Universe?
Cosmic Dawn and the Epoch of Reionization
  How and when did the first stars and galaxies form?

## Slide 10: Delivering SKA Observatory
Feb 2021: SKAO born
June 2021: SKAO Council approved the Construction Proposal and the SKAO Establishment and Delivery Plan
July 2021: Construction activities began
Sept 2022: 42 contracts awarded, total cost ~€200M; more major contracts being prepared

## Slide 11: Cost Estimate
Design Baseline | April 2021 | Provided through annual contributions |  |  | 
Total Cost (€M) (June 2021) | Capital cost of construction (€M) | Construction Support Budget (€M) | Observatory Operations & Business-Enabling Functions (€M) | Observatory Development Programme (€M) | Funding Period
 | (880 + 237) 1117 | (142+38) 180 |  |  | 
2017 | 1297 |  | 679 | 41 | 2021-2030
China’s contribution: 8%

## Slide 12: Construction Strategy
Target: the SKA Baseline Design (197 Mid dishes; 512 Low stations: AA4)
Not all funding yet secured, therefore follow Staged Delivery Plan (AA*)
First Milestone: Develop the earliest possible working demonstration of the architecture and supply chain (AA0.5).
Then maintain a continuously working and expanding facility until achieve the baseline design.
Milestone Event | SKA-Mid (date) | SKA-Low (date)
AA0.5 | 2024 Jul | 2024 May
AA1 | 2025 Sep | 2025 May
AA2 | 2026 Jul | 2026 Jul
AA* | 2027 Jun | 2027 Aug
Operations Readiness Review | 2027 Aug | 2027 Oct
End of Construction | 2028 Jul | 2028 Jul

## Slide 13: Construction Photos

## Slide 14: Recent Prototype and Construction Progress
Band 5a/5b feeds
5 – 15 GHz
Band 5 Digitiser
2 x 2.5 GHz
SKA-MP Prototype
First SKA dish foundations
Improved dish stiffness
and pointing
AAVS2

## Slide 22: SKAO vehicles now in both Austalia and South Africa

## Slide 23: South Africa: interim Science Operations Centre, Cape Town; architect’s view of Engineering Operations Centre in Klerefontein
SOC: open mid-October
EOC: Klerefontein

## Slide 24: Australia: interim SOC, Perth : interim EOC in Geraldton
Interim EOC Geraldton

## Slide 25: Current key challenges
Impact of external factors (inflation, labour shortages, supply chains) on construction costs and schedules: working with Council and member states to mitigate
Pace of engagement in some of aspiring Member governments, potential for mis-alignment with the construction schedule.
There is the standard list of items we watch and manage carefully, e.g.:
  Residual design processes
  Spectrum management, especially mega-constellations
  Land access timescales
  Stakeholder management (local and international)
  ......

## Slide 26
Photo by: Trevor Dobson CC BY-NC-ND 2.0
Notes: One of the things that can happen is that beautiful astrophotography pictures like this one from the Pinnacles in Western Australia, could become something like this. (click)

## Slide 27: Summary
Construction activities are proceeding at pace; residual design issues are being dealt with professionally and expeditiously
Level of risk for the project has increased due to the global situation; mitigations are planned, but they require the commitment of additional resources from Members and the accession of new Members.
SKAO presence in the site host countries is a major positive milestone
SKAO’s reputation and global visibility is growing substantially and positively.